## Slide 1: Mobile Communications’ Base Stations and Wi-Fi Access Points inside a Cruise Ship
Group 08 Alice Navalho · Beatriz Coelho · Luís Nóbrega
Maria Abrantes · Mónica Ferreira · Rodrigo Esgueira
Instituto Superior Técnico

## Slide 2: Outline
Understanding the Onboard Challenge
Scope, Assumptions and Requirements
Stakeholder
Work Breakdown Structure
RACI Matrix
Resources & Cost Analysis
Schedule
Quality Control Plan
Risk Management
Conclusions

## Slide 3: Understanding the Onboard Challenge
OUR SHIP: MV WORLD VOYAGER
KEY CONNECTIVITY CHALLENGES
200
Passengers
120
Crew members
6
Main decks
Metallic Structure
Satellite Backhaul at Sea
Port Shutdown Requirement
Compartmentalized Layout

## Slide 4
Scope, Assumptions & Requirements
Scope
Assumptions and Constraints
Requirement
Radio-frequency Planning
Base Stations
Port Shutdown
Antennas
Wi-Fi
Backhaul Integration
Deck Documentation
Satellite Provider
Regulation
80; 100; 120 €/h
Shutdown
Deadlines
Aesthetic
Business
Technical
Project Management

## Slide 5: Stakeholders
MV Voyager Telecom Project
7 internal
17 external
24 stakeholders
8 Positive
15 Mixed/Neutral
1 Negative

## Slide 6: Work Breakdown Structure

## Slide 7: RACI Matrix
Code | Activity | Project Leader | Radio. Eng | Reg. Dept | Bus. &Sup | Constr(Ext) | Other
E | Wi-Fi AP Layout & Service Zone Design | A | R | C | C | C | Cybersecurity
L | Regulatory Conformity Analysis | A | C | R | C |  | Reg. Agencies
Q | Install Cabling, Power, Base Stations & Anten- nas | A | C |  |  | R | Capt. & Sec.
Y | Handover & Sign-off | R&A | R |  | I |  | Client

## Slide 8: Resources & Cost Analysis
120 €/hr
- Project Leader
- Radio Eng. Sr.
- Law Officer
100 €/hr
- Radio Eng. (2)
- Regulation Officer
- Finance/Mngm.
Analyst
80 €/hr
- Buying Officer
- Marketing
Specialist
External
External
Material
Constructor Fee (5):
100€/hr
Cybersec. Consult. Fee: 120€/hr
Regulatory & License Fees:
3 500€
Outdoor Antenna: 30 000€
Satellite Sign-Up Fee: 5 000€

## Slide 9: Schedule
58,5 days
High risk region
High risk task
96 908 €

## Slide 10: Quality Control Plan
Checkpoints
Design review
Procurement review
Testing review
Final acceptance
Main criteria
95% coverage
325 users + 20% headroom
Latency < 700 ms
Shutdown < 30 s
Control logic
Verification method
Responsible owner
Corrective action
Bi-weekly EVM review
Notes: Este slide resume o plano de controlo da qualidade do projeto. O objetivo é garantir que a solução de telecomunicações para o MV World Voyager é consistente do ponto de vista técnico e está preparada para a fase seguinte de implementação. O controlo da qualidade é feito em seis checkpoints, desde a revisão do design até à aceitação final.
Os principais aspetos avaliados são a cobertura, a capacidade, o backhaul por satélite, o shutdown em porto, a conformidade dos equipamentos e a documentação final. Por exemplo, queremos assegurar pelo menos 95% de cobertura, capacidade para 325 utilizadores simultâneos com 20% de margem, latência abaixo de 700 milissegundos, perda de pacotes inferior a 1% e desligamento da rede celular em menos de 30 segundos em porto. Cada critério tem um método de verificação, um responsável e uma ação corretiva, e complementamos isso com revisões quinzenais de EVM para acompanhar o impacto na duração e no custo do projeto.

## Slide 11: Risk Management
Impact →
Risk Matrix
Probability →
Mitigate ×5
Avoid ×1
Transfer ×1
Accept ×2
R01
R03
R04
R05
R06
R02
R07
R08
R09
Contingency Reserve
≈ 5,5 d
15 174 €
≈ 7% of the 213 996 € estimate
Expected Delay
Within the 6 days buffer

## Slide 12: Conclusions
Complete and realistic planning package for the MV World Voyager telecommunications deployment.
€214 476 €
Work-packages
229 650 €
Baseline
252 615 €
Budget
WBS with clear deliverable traceability.
PERT and resource leveling supported execution planning.
Risk and quality increased budget realism.
Compliance and logistics matched the marine contexto.
Structured, traceable, and implementation-ready.
+ Contigency Reserve
+ Management Reserve (10 %)
Notes: Em conclusão, este projeto entregou um pacote completo de planeamento para o sistema de telecomunicações do MV World Voyager. O trabalho incluiu o desenho técnico, a WBS, o cronograma, os recursos, os riscos e o plano de qualidade.
O projeto ficou bem estruturado e com boa rastreabilidade, porque cada entregável foi ligado a atividades e requisitos claros. A análise PERT e o nivelamento de recursos ajudaram a tornar o planeamento mais realista.
A duração total do projeto é de 58,5 dias, com 6 dias de ghost buffer para acomodar a contingency reserve. No final, o orçamento ficou em 213.996 euros de estimativa, 227.912 euros de cost baseline e 250.703 euros de budget total.